## Product Backlog- HU
Product Backlog - Matrix frame of work HU
ITEM | PROBLEM | What (NEED) | WHAT FOR (SOLUTION) | FOR WHOM(USER) | AS (DESCRIPTION OF TASKS) | MAE BY (PROG. RESP.) | HOW LONG (ESTIMATED IN HRS) | DATE OF DELIVERY | PRIORIRY | STATUS | TEST (AS VERIFIED) | COMMENTS | STORY NAME
REQ001 | Product entry is required | Add Prodcuts | Registration of products in inventory | Administrator | You enter the module to add products, click and enter the information of the products. The system calculates the business rules(VAT calculation, unit and total profit calculation, discount calculation) | Mateo Loachamin | 2 | 2022-11-17 | Alta | Terminado | The interface shows the screen to add products | It is necessary that the system allows to correctly add the data to the database | Add Products to the system
REQ002 | Inventory listing requiered | List Inventory | Review inventory products | Administrator | Enter the product list module, click enter, the application displays the list of stored products | Erick Maldonado | 2 | 2022-11-17 | Alta | Terminado | The interface shows the added products | It is required to verify the information, when displaying the stored data | List Products to the system
REQ003 | Product infromation needs to updated | update Products | Let me update the inventory information | Administrator | Inventory is entered, product edit is clicked, data is update, information is saved | Diego Mantilla | 2 | 2022-11-17 | Alta | Terminado | The interface shows the screen to update products | It is necessary that the system update correctly to the database | Update Products to the system
REQ004 | Allow to delete products | delete Products | Remove items from inventory | Administrator | The inventory is entered, the product to be eliminated is chosen, the product to be eliminated is clicked, the system redirtects to the index | Ligia Maldonado | 2 | 2022-11-17 | Alta | Terminado | The interface remove the products | It is required to verify that the information, has been remove the database | Eliminar Products to the system
[9 empty] | Alta | No iniciado
[9 empty] | Media | En proceso
[9 empty] | Baja | Terminado
Atrasado

## User Stories
USER STORIES (HU) iSoftware.ec
| ITEM |  | USERNAME |  | STATUS
| REQ004 |  | Administrator |  | Terminado
| TIME |  | PRIORITY |  | PROG. RESP
| 2 |  | Alta |  | Ligia Maldonado
| WHAT | delete Products |  | PARA QUE | Remove items from inventory |  | COMO | The inventory is entered, the product to be eliminated is chosen, the product to be eliminated is clicked, the system redirtects to the index
| NAME STORY |  | Eliminar Products to the system
| TEST |  | The interface remove the products |  |  | COMMENTS | It is required to verify that the information, has been remove the database