## Product Backlog- HU
Product Backlog - Matrix frame of work HU
ITEM | PROBLEM | What (NEED) | WHAT FOR (SOLUTION) | FOR WHOM(USER) | AS (DESCRIPTION OF TASKS) | MAE BY (PROG. RESP.) | HOW LONG (ESTIMATED IN HRS) | DATE OF DELIVERY | PRIORIRY | STATUS | TEST (AS VERIFIED) | COMMENTS | STORY NAME
REQ01 | Product entry is required | Add Prodcuts | Registration of products in inventory | Administrator | You enter the module to add products, click and enter the information of the products. The system calculates the business rules(subtotal, total_iva,unit:profit,total_profit) | Mateo Loachamin | 3 | 2022-12-07 | Alta | Terminado | The interface shows the screen to add products | It is necessary that the system allows to correctly add the data to the database | Add Products to the system
REQ02 | Inventory listing requiered | List Products | Review inventory products | Administrator | Enter the product list module, click enter, the application displays the list of stored products | Mateo Loachamin | 3 | 2022-12-07 | Alta | Terminado | The interface shows the added products | It is required to verify the information, when displaying the stored data | List Products to the system
REQ03 | Product infromation needs to updated | Update Products | Let me update the inventory information | Administrator | Inventory is entered, product edit is clicked, data is update, information is saved | Mateo Loachamin | 3 | 2022-12-07 | Alta | Terminado | The interface shows the screen to update products | It is necessary that the system update correctly to the database | Update Products to the system
REQ04 | Allow to delete products | Delete Products | Remove items from inventory | Administrator | The inventory is entered, the product to be eliminated is chosen, the product to be eliminated is clicked, the system redirtects to the index | Mateo Loachamin | 3 | 2022-12-07 | Alta | Terminado | The interface remove the products | It is required to verify that the information, has been remove the database | Delete Products to the system
REQ05 | User entry is requiered | Add User | Registration of users | Administrator | You enter the module to add user, click and enter the information of the user. | Diego Mantilla | 3 | 2022-12-07 | Media | Terminado | The interface shows the screen to add products | It is necessary that the system allows to correctly add the data to the database | Add Client to the system
REQ06 | Users listing requiered | List Users | Review users | Administrator | Enter the User list module, click enter, the application displays the list of users | Diego Mantilla | 3 | 2022-12-07 | Media | Terminado | The interface shows the added users | It is required to verify the information, when displaying the stored data | List Clients to the system
REQ07 | User infromation needs to updated | Update Users | Let me update the user information | Administrator | User is entered, user edit is clicked, data is update, information is saved | Diego Mantilla | 3 | 2022-12-07 | Media | Terminado | The interface shows the screen to update users | It is necessary that the system update correctly to the database | Update Client to the system
REQ08 | Allow to delete User | Delete User | Remove user | Administrator | The user is entered, the user to be eliminated is chosen, the user to be eliminated is clicked, the system redirected to the index | Diego Mantilla | 3 | 2022-12-07 | Media | Terminado | The interface remove the users | It is required to verify that the information, has been remove the database | Delete Client to the system
REQ09 | Order entry is required | Add Order | Registration of new orders | Administrator | Enter the order information to add a new order in the database, until the discount value, the system calculates the discount price | Erick Maldonado | 3 | 2022-12-07 | Alta | Terminado | The interface shows the screen to add order | It is necessary to check if the order it's correctly added to the database | Add orders to the system
REQ10 | Order listing requiered | List Orders | Review the list of orders | Administrator | Enter the order list module and the system shows up a list of orders saved in the database | Erick Maldonado | 3 | 2022-12-07 | Alta | Terminado | The interface shows the added orders | It is necessary to check if all of the orders are showed, from the database | List orders to the system
REQ11 | Order infromation needs to updated | Update Orders | Allow to update the orders information | Administrator | An order is edited, the information about the order it's modified and saved in the database. | Erick Maldonado | 3 | 2022-12-07 | Alta | Terminado | The interface shows the screen to update order | It is necessary to check if the order it's correctly updated to the database | Update orders to the system
REQ12 | Allow to delete orders | Delete Orders | Remove an order from the databes | Administrator | An order it's selected, searched by the order's id and deleated from the database | Erick Maldonado | 3 | 2022-12-07 | Alta | Terminado | The interface remove the order | It is necessary to check if the order it's correctly deleated to the database | Delete orders to the system
REQ13 | Invoice entry is required | Add Invoice | Registration of new Invoices | Administrator | Enter the order information to add a new Invoice in the database. | Ligia Maldonado | 3 | 2022-12-07 | Media | Terminado | The interface shows the screen to add invoice | It is necessary to check if the order it's correctly added to the database | Add invoice to the system
REQ14 | Invoice listing requiered | List Invoices | Review the list of Invoices | Administrator | Enter the order list module and the system shows up a list of Invoices saved in the database | Ligia Maldonado | 3 | 2022-12-07 | Media | Terminado | The interface shows the added invoice | It is necessary to check if all of the orders are showed, from the database | List invoices to the system
REQ15 | Invoice infromation needs to updated | Update Invoice | Allow to update the Invoice information | Administrator | An Invoice is edited, the information about the Invoice it's modified and saved in the database. | Ligia Maldonado | 3 | 2022-12-07 | Media | Terminado | The interface shows the screen to update invoice | It is necessary to check if the order it's correctly updated to the database | Update invoice to the system
REQ16 | Allow to delete Invoice | Delete Invoice | Remove an Invoice from the databes | Administrator | An Invoice it's selected, searched by the Invoices id and deleated from the database | Ligia Maldonado | 3 | 2022-12-07 | Media | Terminado | The interface remove the invoice | It is necessary to check if the order it's correctly deleated to the database | Delete invoice to the system
REQ17 | Invoice entry is required | Add Distributor | Registration of new Distributor | Administrator | Enter the order information to add a new Distributor in the database. | Diego Mantilla | 3 | 2023-01-30 | Media | Terminado | The interface shows the screen to add Distributor | It is necessary to check if the order it's correctly added to the database | Add Distributor to the system
REQ18 | Invoice listing requiered | List Distributor | Review the list of Distributor | Administrator | Enter the order list module and the system shows up a list of Distributor saved in the database | Diego Mantilla | 3 | 2023-01-30 | Media | Terminado | The interface shows the added Distributor | It is necessary to check if all of the orders are showed, from the database | List Distributor to the system
REQ19 | Invoice infromation needs to updated | Update Distributor | Allow to update the Distributor information | Administrator | An Invoice is edited, the information about the Distributor it's modified and saved in the database. | Diego Mantilla | 3 | 2023-01-30 | Media | Terminado | The interface shows the screen to update Distributor | It is necessary to check if the order it's correctly updated to the database | Update Distributor to the system
REQ20 | Allow to delete Invoice | Delete Distributor | Remove an Distributor from the databes | Administrator | An Invoice it's selected, searched by the Distributor id and deleated from the database | Diego Mantilla | 3 | 2023-01-30 | Media | Terminado | The interface remove the Distributor | It is necessary to check if the order it's correctly deleated to the database | Delete Distributor to the system
REQ16 | Search for a Product | Search Product | Search an Product from the databes | Administrator | An Invoice it's selected, searched by the Product | Mateo Loachamin | 3 | 2022-12-07 | Media | Terminado | The interface shows the added products | It is required to verify the information, when displaying the stored data | Search for a Product
REQ17 | Search for a User | Search User | Search an User from the databes | Administrator | An Invoice it's selected, searched by the User | Diego Mantilla | 3 | 2023-01-30 | Media | Terminado | The interface shows the screen to add Distributor | It is required to verify the information, when displaying the stored data | Search for a User
REQ18 | Search for a Order | Search Order | Search an Order from the databes | Administrator | An Invoice it's selected, searched by the Order | Erick Maldonado | 3 | 2023-01-30 | Media | Terminado | The interface shows the added users | It is required to verify the information, when displaying the stored data | Search for a Order
REQ19 | Search for a Invoice | Search Invoice | Search an Invoice from the databes | Administrator | An Invoice it's selected, searched by the Invoice | Ligia Maldonado | 3 | 2023-01-30 | Media | Terminado | The interface shows the added Orders | It is required to verify the information, when displaying the stored data | Search for a Invoice
REQ20 | Search for a Distributor | Search Distributoruct | Search an Distributoruct from the databes | Administrator | An Invoice it's selected, searched by the ProdDistributoructuct | Diego Mantilla | 3 | 2023-01-30 | Media | Terminado | The interface shows the added Distributor | It is required to verify the information, when displaying the stored data | Search for a Distributor
[9 empty] | Alta | No iniciado
[9 empty] | Media | En proceso
[9 empty] | Baja | Terminado
Atrasado

## User Stories
USER STORIES (HU) iSoftware.ec
| ITEM |  | USERNAME |  | STATUS
| REQ01 |  | Administrator |  | Terminado
| TIME |  | PRIORITY |  | PROG. RESP
| 3 |  | Alta |  | Mateo Loachamin
| WHAT | Add Prodcuts |  | PARA QUE | Registration of products in inventory |  | COMO | You enter the module to add products, click and enter the information of the products. The system calculates the business rules(subtotal, total_iva,unit:profit,total_profit)
| NAME STORY |  | Add Products to the system
| TEST |  | The interface shows the screen to add products |  |  | COMMENTS | It is necessary that the system allows to correctly add the data to the database