## Product Backlog- HU
Product Backlog - Matrix frame of work HU
ITEM | PROBLEM | What (NEED) | WHAT FOR (SOLUTION) | FOR WHOM(USER) | AS (DESCRIPTION OF TASKS) | MAE BY (PROG. RESP.) | HOW LONG (ESTIMATED IN HRS) | DATE OF DELIVERY | PRIORIRY | STATUS | TEST (AS VERIFIED) | COMMENTS | STORY NAME
REQ001 | Product entry is required | Add Prodcuts | Registration of products in inventory | Administrator | You enter the module to add products, click and enter the information of the products. The system calculates the business rules(VAT calculation, unit and total profit calculation, discount calculation) | Mateo Loachamin | 2 | 2022-11-17 | Alta | Terminado | The interface shows the screen to add products | It is necessary that the system allows to correctly add the data to the database | Add Products to the system
REQ002 | It is required to determine the business rules | Implement business rules | Perform calculations for each business | Administrator | Whe entering the products, the system performs the calculation of: Calculation of distributed price, calcularion of VAT, unit profit, total profit, customer discount | All teams | 6 | 2022-11-17 | Alta | Terminado | It is verified by entering to see the list of added products | Its is recommended to validate that the operations are correct | Implement business rules in the application
REQ003 | See the products | List Products | Review inventory products | Administrator | Enter the product list module, click enter, the application displays the list of stored products | Erick Maldonado | 2 | 2022-11-17 | Alta | Terminado | The interface shows the added products | It is required to verify the information, when displaying the stored data | List Products to the system
REQ004 | Adding users is required | Add Users | User registration in the system | Administrator | You enter the module to add products, click and enter the information of the products. The system calculates the business rules(VAT calculation, unit and total profit calculation, discount calculation) | Diego Mantilla | 2 | 2022-11-17 | Alta | Terminado | The interface shows the screen to add users | It is necessary that the system allows to correctly add the data to the database | Add Users to the system
REQ005 | See the users | List Users | Rerview the users registred in the system | Administrator | Enter the user list module, click enter, the application displays the list of stored users | Ligia Maldonado | 2 | 2022-11-17 | Alta | Terminado | The interface shows the added users | It is required to verify the information, when displaying the stored data | List Users to the system
[9 empty] | Alta | No iniciado
[9 empty] | Media | En proceso
[9 empty] | Baja | Terminado
Atrasado

## User Stories
USER STORIES (HU) iSoftware.ec
| ITEM |  | USERNAME |  | STATUS
| REQ005 |  | Administrator |  | Terminado
| TIME |  | PRIORITY |  | PROG. RESP
| 2 |  | Alta |  | Ligia Maldonado
| WHAT | List Users |  | PARA QUE | Rerview the users registred in the system |  | COMO | Enter the user list module, click enter, the application displays the list of stored users
| NAME STORY |  | List Users to the system
| TEST |  | The interface shows the added users |  |  | COMMENTS | It is required to verify the information, when displaying the stored data